## Timeline Feb-Apr 2026
Sr. | Task | Deadline | Sub Task | Sub Task Deadline | Responsible | Project | Priority | Status | Progress | Key Remarks / Issues | Escalation
1 | PHP, IoT & Foundations | 27-Feb-2026 | Environment setup (Laravel, Composer, MySQL, VS Code, Git) | 25-Feb-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Foundation phase closed successfully before March implementation work started. | -
|  |  | PHP basics practice (forms, functions, DB connection) | 26-Feb-2026
|  |  | IoT fundamentals study (smart homes, industrial sensors, energy meters) | 26-Feb-2026
|  |  | Initial MySQL project structure planning | 27-Feb-2026
|  |  | First sample/sensor data entry into DB | 27-Feb-2026
2 | Database Design & Migrations | 03-Mar-2026 | Create devices table | 02-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Core schema completed for devices, history, and latest-state caching. | -
|  |  | Create meter_readings table | 03-Mar-2026
|  |  | Create latest_meter_states table | 03-Mar-2026
|  |  | Add foreign keys, indexes, and duplicate-protection rules | 03-Mar-2026
3 | MQTT Integration Setup | 05-Mar-2026 | Install MQTT client package | 04-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Broker connectivity established from Laravel. | -
|  |  | Configure broker connection and credentials | 04-Mar-2026
|  |  | Test broker connectivity from Laravel | 05-Mar-2026
4 | MQTT Consumer Development | 06-Mar-2026 | Create mqtt:consume-meter command | 06-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Consumer command created and verified with live payload reception. | -
|  |  | Subscribe to active device topic(s) | 06-Mar-2026
|  |  | Receive MQTT payloads | 06-Mar-2026
|  |  | Parse JSON payload into reading fields | 06-Mar-2026
5 | Data Storage Implementation | 09-Mar-2026 | Store incoming meter data in meter_readings | 09-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | End-to-end MQTT to DB path completed. | -
|  |  | Update latest_meter_states on every valid reading | 09-Mar-2026
|  |  | Update devices.last_seen_at | 09-Mar-2026
6 | Debugging & Issue Fixing | 11-Mar-2026 | Fix device/topic matching issues | 10-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Initial stabilization completed across ingestion and dashboard flow. | -
|  |  | Fix route/data issues affecting dashboard reads | 11-Mar-2026
|  |  | Resolve event/data display inconsistencies | 11-Mar-2026
7 | Initial Dashboard Integration | 13-Mar-2026 | Fetch data from API/DB for dashboard | 12-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Single-device dashboard delivered with realtime behavior. | -
|  |  | Show live KPIs, charts, and readings table | 13-Mar-2026
|  |  | Verify realtime updates via Reverb/Echo | 13-Mar-2026
8 | System Testing (Single Device) | 19-Mar-2026 | Test MQTT -> DB -> Dashboard end-to-end flow | 17-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 95% | Core single-device flow validated; structured edge-case logging moved to later improvement work. | -
|  |  | Validate stored data against source feed | 18-Mar-2026
|  |  | Verify dashboard behavior after restart / reload | 19-Mar-2026
9 | System Review & Next-Phase Planning | 20-Mar-2026 | Review completed pilot architecture | 20-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Pilot review completed before Eid break; multi-device backlog defined. | -
|  |  | Identify multi-device and validation gaps | 20-Mar-2026
|  |  | Prepare next implementation direction | 20-Mar-2026
10 | Eid Holiday Break / Non-Working Window | 23-Mar-2026 | Eid-ul-Fitr holiday | 21-Mar-2026 | - | IoT Webapp Development | - | Holiday | - | Public holidays excluded from the working schedule. | -
|  |  | Eid-ul-Fitr holiday | 22-Mar-2026
|  |  | Pakistan Day / Eid public holiday overlap | 23-Mar-2026
11 | Multi-Device Support & Testing | 26-Mar-2026 | Review consumer behavior for all active devices | 24-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Confirmed that ingestion must remain global while display stays per-device. | -
|  |  | Verify per-device readings API direction | 25-Mar-2026
|  |  | Plan multi-device DB/UI behavior | 26-Mar-2026
12 | Data Validation & Normalization | 30-Mar-2026 | Review invalid JSON handling strategy | 27-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 90% | Validation strategy reviewed; structured logging remained a later enhancement. | -
|  |  | Review duplicate payload handling | 30-Mar-2026
|  |  | Normalize latest-state update logic | 30-Mar-2026
13 | Latest State & API Development | 01-Apr-2026 | Improve latest-state consistency | 31-Mar-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Per-device readings endpoint and latest-state behavior stabilized. | -
|  |  | Fix dashboard readings API routing behavior | 01-Apr-2026
|  |  | Align API output with dashboard needs | 01-Apr-2026
14 | Dashboard Reliability & Error Handling | 03-Apr-2026 | Repair stale realtime dashboard wiring | 02-Apr-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Dashboard polling and realtime flow made reliable for pilot usage. | -
|  |  | Improve background refresh behavior | 03-Apr-2026
|  |  | Strengthen failed-refresh and bad-state handling | 03-Apr-2026
15 | Documentation, Setup & Handoff | 08-Apr-2026 | Clarify .env usage and MySQL-based setup | 06-Apr-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Setup guidance and project continuity documents completed. | -
|  |  | Write run instructions and verification flow | 07-Apr-2026
|  |  | Create full project handoff documentation | 08-Apr-2026
16 | PPT Analysis, Feasibility & Roadmap | 10-Apr-2026 | Analyze full PPT project scope vs current codebase | 09-Apr-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Project direction updated from pilot dashboard to platform roadmap. | -
|  |  | Assess whether full platform is achievable | 09-Apr-2026
|  |  | Build weekly roadmap and Week 1 verification plan | 10-Apr-2026
17 | Multi-Meter Planning & UX Definition | 14-Apr-2026 | Define frontend add/remove device behavior | 13-Apr-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Final UX model approved: store all devices, show only selected device. | -
|  |  | Define delete cascade expectations | 13-Apr-2026
|  |  | Define selected-device-only dashboard behavior | 14-Apr-2026
18 | Multi-Meter Implementation | 21-Apr-2026 | Add selectable dashboard controller flow | 15-Apr-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | In Progress | 90% | Implemented multi-meter dashboard selection and device management; local DB-backed tests require pdo_sqlite to run fully. | If full local automated DB tests are required, install the pdo_sqlite PHP extension.
|  |  | Add device management route/controller/page | 16-Apr-2026
|  |  | Add create/delete API flow with comments | 17-Apr-2026
|  |  | Add dashboard selector and realtime filtering | 20-Apr-2026
|  |  | Add tests and verification updates | 21-Apr-2026
19 | Final UAT / Closing Window | 24-Apr-2026 | Verify old and new meter visibility in UI | 22-Apr-2026 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Pending | 0% | Final user validation window for meter visibility, add/delete flow, and selected-device-only behavior. | If older devices do not appear in UI, verify devices.type = meter and confirm is_active where applicable.
|  |  | Verify add/delete flow plus consumer restart operational step | 23-Apr-2026
|  |  | Verify selected-device-only dashboard with all-device background ingestion | 24-Apr-2026