## IoT Product
Single Phase IoT Smart Meter — R&D Tracking Sheet
S.no | Product | Phase | Milestone | Use Case | Priority | KPI | Target | Current Value | Status (R/Y/G/P) | Daily Task | Owner | Start Date | Deadline | Evidence
1 | Single Phase IoT Smart Meter | Testing (Inprogress) | Make fully Functional & Stability Validation | Real time Electrical Data with Mulitmeter | High | Accuracy ≤ ±1% | Achieved | Error 0.5% | G | Completed | Inaam Ullah & M.Ayan Alam | 2026-01-12 | 2026-01-21 | Real time data from Multimeter
|  |  |  | Accurate Energy Monitoring & comapre with WAPDA meter | Medium | Energy Error ≤ ±1% | In progress | Energy Error 19% (Inprogress) | Y | 1. Monitor the Readings 2. Enhancement of firmware | M.Ayan Alam | 2026-01-22 | 2026-03-19 | Comparison Sheet
|  |  |  | Reliable MQTT | High | MQTT Publish Every 5 sec | Achieved | Improved | G | Completed |  | 2026-01-22 | 2026-02-10 | Mqtt Dashboard
|  |  |  | Stable WiFi | Medium | WiFi Reconnect < 15 sec | In progress | Improved (In progress) | Y | Troubleshooting new problems |  | 2026-02-12 | 2026-03-19 | Real time live data viewed
|  |  |  | Web OTA & Auto Restart | High | 24hr Stable Operation | In progress | In progress | Y | Troubleshooting new problems |  | 2026-02-12 | 2026-03-19 | Update firmware using OTA
|  |  |  | URL OTA | Low | 7 Days auto checking for updates | Planed work | Planed work | P | Not Commenced |  | - | - | -
Three Phase IoT Smart Meter — R&D Tracking Sheet
S.no | Product | Phases | Milestones | Use Case | Priority | KPI | Target | Current Value | Status (R/Y/G/P) | Daily Task | Owner | Start Date | Deadline | Evidence
2 | Three Phase IoT Smart Meter | 1) Research | a) Previous Meter Observation | Analyze previous meter design and working | Medium | Design Understanding | Completed | Completed | G | Study previous meter circuitry | Inaam Ullah & M. Ayan Alam | 2025-10-26 | 2025-10-28 | Research Notes
|  |  | b) Components Research | Identify suitable components for 3-phase meter | High | Component Selection | Completed | Completed | G | Research ICs & sensors |  | 2025-11-18 | 2025-11-21 | Component Comparison Sheet
|  |  | c) Circuitry Research | Study 3-phase measurement circuitry | High | Circuit Architecture | Completed | Completed | G | Circuit simulation & analysis |  | 2025-11-24 | 2025-11-28 | Circuit Notes
|  | 2) Procurement | Purchase Components | Purchase additional electronic components | Medium | Component Availability | Completed | Completed | G | Visit to Market for purchasing components |  | 2026-01-04 | 2026-01-29 | Purchase components from local market and ordered one from china
|  | 3) Lab Testing of Components | Component Selection & Testing | Testing of components in lab | High | Hardware Compatibility | Completed | Completed | G | Hardware validation |  | 2026-01-30 | 2026-02-11 | Verification of Components working properly
|  | 4) Hardware Testing | Breadboard Circuit Testing | Validate circuit on breadboard | High | Stable working of meter | In Progress | Testing and verifying that circuit have no issues | Y | Monitor Volatge and current values | Inaam Ullah | 2026-02-12 | 2026-03-19 | Breadboard Testing of circuit
|  | 5) Firmware Development | Firmware development & Testing | Develop and test firmware | High | Stable Energy Monitoring & Firmware Stability | In Progress | Development and enhancment ongoing | Y | Write & debug firmware | Inaam Ullah | 2026-02-12 | 2026-03-19 | working on firmware
|  | 6) Circuit Finalization | Circuit Simulation & Finalization | Finalize hardware circuit | High | Circuit Accuracy | Planned | Planned | p | Finalize circuit diagram | Inaam Ullah | 2026-03-30 | 2026-04-02 | Final Schematic
|  | 7) PCB Design | PCB Layout Designing | Convert schematic into PCB layout | High | PCB Layout Completion | Planned | Planned | P | PCB routing & design | Inaam Ullah | 2026-04-03 | 2026-04-15 | making of PCB layout
|  | 8) Send Designs to China | Send Design to JLCPCB | Order PCB fabrication | Medium | PCB Order Submission | Planned | Planned | P | Submit PCB design for order | Inaam Ullah | 2026-04-14 | 2026-04-15 | Placement of PCB fabrication order to JLC PCB
|  | 9)Manufacturing | PCB Fabrication | Receive fabricated PCBs | Medium | PCB Delivery | Planned | Depends on Shipment | P | Track shipment | Inaam Ullah | - | - | Track & Check for shipment if its stuck at customs or not
|  | 10) Assembly | Soldering Components | Assemble components on PCB | High | Placement of components on PCB board | Planned | Planned | P | PCB soldering | M. Ayan Alam | After PCB Arrival | - | Soldering of components on PCB board
|  | 11) System & Accuracy Testing | a) Reading Comparison with WAPDA b) Make fully Functional & Stability Validation | Real time Electrical Data with Mulitmeter | High | Accuracy ≤ ±1% | Planned | Planned | P | Comparing real time reading | Inaam Ullah | After PCB Arrival | - | Real time data from Multimeter
|  |  |  | Compare readings with reference meters WAPDA | High | Accuracy ≤ ±1% | Planned | Planned | P | Comparing real time readings with WAPDA | M Ayan Alam | After PCB Arrival | - | Comparison Sheet
|  |  |  | Accurate Energy Monitoring & comapre with WAPDA meter | Medium | Energy Error ≤ ±1% | Planned | Planned | P | Monitor the Readings Enhancement of firmware | Inaam Ullah | After PCB Arrival | - | Comparison Sheet
|  |  |  | Reliable MQTT | High | MQTT Publish Every 5 sec | Planned | Planned | P | Working on Firmware | Inaam Ullah | After PCB Arrival | - | Mqtt Dashboard
|  |  |  | Stable WiFi | Medium | WiFi Reconnect < 15 sec | Planned | Planned | P | Troubleshooting new problems | Inaam Ullah | After PCB Arrival | - | Real time live data viewed
|  |  |  | Web OTA & Auto Restart | High | 24hr Stable Operation | Planned | Planned | P | Troubleshooting new problems | Inaam Ullah | After PCB Arrival | - | Update firmware using OTA
|  |  |  | URL OTA | Low | 7 Days auto checking for updates | Planned | Planned | P | Not Commenced | Hammaad | - | - | -
Smart IoT Water Management System — R&D Tracking Sheet
S.no | Product | Phases | Milestones | Use Case | Priority | KPI | Target | Current Value | Status (R/Y/G/P) | Daily Task | Owner | Start Date | Deadline | Evidence
3 | Smart IoT Water Management System | 1) Observing & Troubleshooting | a) Previous System Observation b) Power Issue Resolution c) Sensor Integration checking | a) Study previous WMS design and check working b) Resolve power supply issues with electrician c) Checked device and sensor integration with app | High | a) System Understanding b) Stable Power Supply c) Sensor Communication | Achieved | a) Completed b) Completed (Needs upgrade) c) it is not working | G | a) Observe previous WMS operation b) Diagnose power faults c) Debug sensor connections | Inaam Ullah & M. Ayan Alam | 2026-01-21 | 2026-01-23 | a) Inspected the previous Circuit but it is not working
[12 empty] | 2026-02-09 | 2026-02-17 | b) Fault detected as HLK was burned Out c) Checking and working on various sensors and ensuring its proper working
|  | 2) Research | Hardware Upgrade Research | Research improved components for Smart WMS | High | Hardware Improvement Plan | Finding best components for making protected and operational circuit | In progress | Y | Component research and selection of new components | M. Ayan Alam | 2026-03-12 | 2026-03-13 | Component Comparison and selecting the best component
|  | 3) Circuit Design | a) Component Finalization | Selection of best suitable components and finalize circuitry | High | Component Compatibility | Planned | Planned | P | Finalize circuit components | Inaam Ullah | 2026-03-16 | 2026-03-17 | Finalization of Components for cicuit designing
|  |  | b) Circuit Simulation | Simulate and validate circuit design | High | Circuit Stability | Planned | Planned | P | Design circuit on Altium Designer | M. Ayan Alam | 2026-03-18 | After Eid-2026 | Verification of circuit diagram
|  | 4) Firmware Development & Hardware Testing | a) Firmware Upgrade & Testing | Develop firmware for Smart IoT WMS | High | Firmware Stability | Planned | Planned | P | Write & test firmware | M. Ayan Alam | 2026-04-01 | 2026-04-21 | Upgradation of firmware and checking it by uploading it to Breadboard designed Circuitry
|  |  | b) Breadboard Testing | Test circuit functionality on breadboard |  | Stable Sensor Readings | Planned | Planned | P | Monitor water sensor data | M. Ayan Alam
|  | 5) PCB Design | PCB Schematics & Layout | Convert circuit into PCB design | High | PCB Layout Completion | Planned | Planned | P | PCB Design routing and adjustment | T.B.D | 2026-04-22 | 2026-05-08 | PCB Design Files
|  | 8) Send Designs to China | Send Design to JLCPCB | Upload gerber files and order PCBs | Medium | PCB Order Submission | Planned | Planned | P | Submit PCB design for order | Inaam Ullah | 2026-05-11 | 2026-05-12 | Placement of PCB fabrication order to JLC PCB
|  | 7) Manufacturing | PCB Fabrication | Receive fabricated PCBs | Medium | PCB Delivery | Planned | Depends on Shipment | P | Track shipment | Inaam Ullah | - | - | Track & Check for shipment if its stuck at customs or not
|  | 8) Assembly | PCB Soldering | Assemble electronic components | High | Placement of components on PCB board | Planned | Planned | P | Solder components on PCB | M. Ayan Alam | After Receiving PCBs | - | Assemble hardware design availibilty
|  | 9) System Testing | Cloud Testing & Observation | Test data transmission to cloud | High | Reliable IoT Data Transmission | Planned | Planned | P | Monitor MQTT/cloud data | Inaam Ullah | After Soldering PCBs | - | data on MQTT Dashboard
|  | 10) System & Accuracy Testing | Make fully Functional & Stability Validation | Real time testing of its automatic and manual mode | High | Accuracy ≤ ±1% | Planned | Planned | P | Check Status and update firmware | M. Ayan Alam | - | - | Check sheets
|  |  |  | Accurate water flow and level readings | High | Accuracy ≤ ±1% | Planned | Planned | P | Check readings and update firmware | M. Ayan Alam | - | - | Reading sheets
|  |  |  | Reliable MQTT | Medium | MQTT Publish Every 5 sec | Planned | Planned | P | Working on Firmware | M. Ayan Alam | - | - | Mqtt Dashboard
|  |  |  | Stable WiFi | Medium | WiFi Reconnect < 15 sec | Planned | Planned | P | Troubleshooting new problems | M. Ayan Alam | - | - | Real time live data viewed
|  |  |  | Web OTA & Auto Restart | Medium | 24hr Stable Operation | Planned | Planned | P | Troubleshooting new problems | M. Ayan Alam | - | - | Update firmware using OTA
|  |  |  | URL OTA | Medium | 7 Days auto checking for updates | Planned | Planned | P | Not Commenced | Hammaad Ahmad | - | - | -
|  | 11) IoT Integration | IoT App Integration | Integrate WMS with IoT application | High | Live Data Visualization | Pending | Pending | P | Not Commenced | Hammaad Ahmad | - | - | Data on IoT Dashboard
Muhammad Taqi — IoT Engineer ¦ Handover from Inaam Ullah (left the company) — R&D Tracking Sheet
S.no | Product | Phase | Milestone | Use Case | Priority | KPI | Target | Current Value | Status (R/Y/G/P) | Daily Task | Owner | Start Date | Deadline | Evidence
1 | Single Phase IoT Smart Meter | Testing (Inprogress) | Make fully Functional & Stability Validation | Real time Electrical Data with Mulitmeter | High | Accuracy ≤ ±1% | Achieved | Error 0.5% | G | Completed | Muhammad Taqi & M. Ayan Alam | 2026-01-12 | 2026-01-21 | Real time data from Multimeter
2 | Three Phase IoT Smart Meter | 1) Research | a) Previous Meter Observation | Analyze previous meter design and working | Medium | Design Understanding | Completed | Completed | G | Study previous meter circuitry | Muhammad Taqi & M. Ayan Alam | 2025-10-26 | 2025-10-28 | Research Notes
3 | Three Phase IoT Smart Meter | 4) Hardware Testing | Breadboard Circuit Testing | Validate circuit on breadboard | High | Stable working of meter | In Progress | Testing and verifying that circuit have no issues | Y | Monitor Volatge and current values | Muhammad Taqi | 2026-02-12 | 2026-03-19 | Breadboard Testing of circuit
4 | Three Phase IoT Smart Meter | 5) Firmware Development | Firmware development & Testing | Develop and test firmware | High | Stable Energy Monitoring & Firmware Stability | In Progress | Development and enhancment ongoing | Y | Write & debug firmware | Muhammad Taqi | 2026-02-12 | 2026-03-19 | working on firmware
5 | Three Phase IoT Smart Meter | 6) Circuit Finalization | Circuit Simulation & Finalization | Finalize hardware circuit | High | Circuit Accuracy | Planned | Planned | p | Finalize circuit diagram | Muhammad Taqi | 2026-03-30 | 2026-04-02 | Final Schematic
6 | Three Phase IoT Smart Meter | 7) PCB Design | PCB Layout Designing | Convert schematic into PCB layout | High | PCB Layout Completion | Planned | Planned | P | PCB routing & design | Muhammad Taqi | 2026-04-03 | 2026-04-15 | making of PCB layout
7 | Three Phase IoT Smart Meter | 8) Send Designs to China | Send Design to JLCPCB | Order PCB fabrication | Medium | PCB Order Submission | Planned | Planned | P | Submit PCB design for order | Muhammad Taqi | 2026-04-14 | 2026-04-15 | Placement of PCB fabrication order to JLC PCB
8 | Three Phase IoT Smart Meter | 9)Manufacturing | PCB Fabrication | Receive fabricated PCBs | Medium | PCB Delivery | Planned | Depends on Shipment | P | Track shipment | Muhammad Taqi | - | - | Track & Check for shipment if its stuck at customs or not
9 | Three Phase IoT Smart Meter | 11) System & Accuracy Testing | a) Reading Comparison with WAPDA b) Make fully Functional & Stability Validation | Real time Electrical Data with Mulitmeter | High | Accuracy ≤ ±1% | Planned | Planned | P | Comparing real time reading | Muhammad Taqi | After PCB Arrival | - | Real time data from Multimeter
10 | Three Phase IoT Smart Meter | 11) System & Accuracy Testing | a) Reading Comparison with WAPDA b) Make fully Functional & Stability Validation | Accurate Energy Monitoring & comapre with WAPDA meter | Medium | Energy Error ≤ ±1% | Planned | Planned | P | Monitor the Readings Enhancement of firmware | Muhammad Taqi | After PCB Arrival | - | Comparison Sheet
11 | Three Phase IoT Smart Meter | 11) System & Accuracy Testing | a) Reading Comparison with WAPDA b) Make fully Functional & Stability Validation | Reliable MQTT | High | MQTT Publish Every 5 sec | Planned | Planned | P | Working on Firmware | Muhammad Taqi | After PCB Arrival | - | Mqtt Dashboard
12 | Three Phase IoT Smart Meter | 11) System & Accuracy Testing | a) Reading Comparison with WAPDA b) Make fully Functional & Stability Validation | Stable WiFi | Medium | WiFi Reconnect < 15 sec | Planned | Planned | P | Troubleshooting new problems | Muhammad Taqi | After PCB Arrival | - | Real time live data viewed
13 | Three Phase IoT Smart Meter | 11) System & Accuracy Testing | a) Reading Comparison with WAPDA b) Make fully Functional & Stability Validation | Web OTA & Auto Restart | High | 24hr Stable Operation | Planned | Planned | P | Troubleshooting new problems | Muhammad Taqi | After PCB Arrival | - | Update firmware using OTA
14 | Smart IoT Water Management System | 1) Observing & Troubleshooting | a) Previous System Observation b) Power Issue Resolution c) Sensor Integration checking | a) Study previous WMS design and check working b) Resolve power supply issues with electrician c) Checked device and sensor integration with app | High | a) System Understanding b) Stable Power Supply c) Sensor Communication | Achieved | a) Completed b) Completed (Needs upgrade) c) it is not working | G | a) Observe previous WMS operation b) Diagnose power faults c) Debug sensor connections | Muhammad Taqi & M. Ayan Alam | 2026-01-21 | 2026-01-23 | a) Inspected the previous Circuit but it is not working
15 | Smart IoT Water Management System | 3) Circuit Design | a) Component Finalization | Selection of best suitable components and finalize circuitry | High | Component Compatibility | Planned | Planned | P | Finalize circuit components | Muhammad Taqi | 2026-03-16 | 2026-03-17 | Finalization of Components for cicuit designing
16 | Smart IoT Water Management System | 8) Send Designs to China | Send Design to JLCPCB | Upload gerber files and order PCBs | Medium | PCB Order Submission | Planned | Planned | P | Submit PCB design for order | Muhammad Taqi | 2026-05-11 | 2026-05-12 | Placement of PCB fabrication order to JLC PCB
17 | Smart IoT Water Management System | 7) Manufacturing | PCB Fabrication | Receive fabricated PCBs | Medium | PCB Delivery | Planned | Depends on Shipment | P | Track shipment | Muhammad Taqi | - | - | Track & Check for shipment if its stuck at customs or not
18 | Smart IoT Water Management System | 9) System Testing | Cloud Testing & Observation | Test data transmission to cloud | High | Reliable IoT Data Transmission | Planned | Planned | P | Monitor MQTT/cloud data | Muhammad Taqi | After Soldering PCBs | - | data on MQTT Dashboard

## IoT App
1 | PHP, IoT & Foundations | 2026-02-27 | Environment setup (Laravel, Composer, MySQL, VS Code, Git) | 2026-02-25 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Foundation phase closed successfully before March implementation work started. | -
|  |  | PHP basics practice (forms, functions, DB connection) | 2026-02-26
|  |  | IoT fundamentals study (smart homes, industrial sensors, energy meters) | 2026-02-26
|  |  | Initial MySQL project structure planning | 2026-02-27
|  |  | First sample/sensor data entry into DB | 2026-02-27
2 | Database Design & Migrations | 2026-03-03 | Create devices table | 2026-03-02 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Core schema completed for devices, history, and latest-state caching. | -
|  |  | Create meter_readings table | 2026-03-03
|  |  | Create latest_meter_states table | 2026-03-03
|  |  | Add foreign keys, indexes, and duplicate-protection rules | 2026-03-03
3 | MQTT Integration Setup | 2026-03-05 | Install MQTT client package | 2026-03-04 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Broker connectivity established from Laravel. | -
|  |  | Configure broker connection and credentials | 2026-03-04
|  |  | Test broker connectivity from Laravel | 2026-03-05
4 | MQTT Consumer Development | 2026-03-06 | Create mqtt:consume-meter command | 2026-03-06 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Consumer command created and verified with live payload reception. | -
|  |  | Subscribe to active device topic(s) | 2026-03-06
|  |  | Receive MQTT payloads | 2026-03-06
|  |  | Parse JSON payload into reading fields | 2026-03-06
5 | Data Storage Implementation | 2026-03-09 | Store incoming meter data in meter_readings | 2026-03-09 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | End-to-end MQTT to DB path completed. | -
|  |  | Update latest_meter_states on every valid reading | 2026-03-09
|  |  | Update devices.last_seen_at | 2026-03-09
6 | Debugging & Issue Fixing | 2026-03-11 | Fix device/topic matching issues | 2026-03-10 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Initial stabilization completed across ingestion and dashboard flow. | -
|  |  | Fix route/data issues affecting dashboard reads | 2026-03-11
|  |  | Resolve event/data display inconsistencies | 2026-03-11
7 | Initial Dashboard Integration | 2026-03-13 | Fetch data from API/DB for dashboard | 2026-03-12 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Single-device dashboard delivered with realtime behavior. | -
|  |  | Show live KPIs, charts, and readings table | 2026-03-13
|  |  | Verify realtime updates via Reverb/Echo | 2026-03-13
8 | System Testing (Single Device) | 2026-03-19 | Test MQTT -> DB -> Dashboard end-to-end flow | 2026-03-17 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 95% | Core single-device flow validated; structured edge-case logging moved to later improvement work. | -
|  |  | Validate stored data against source feed | 2026-03-18
|  |  | Verify dashboard behavior after restart / reload | 2026-03-19
9 | System Review & Next-Phase Planning | 2026-03-20 | Review completed pilot architecture | 2026-03-20 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Pilot review completed before Eid break; multi-device backlog defined. | -
|  |  | Identify multi-device and validation gaps | 2026-03-20
|  |  | Prepare next implementation direction | 2026-03-20
10 | Eid Holiday Break | 2026-03-23 | Eid-ul-Fitr holiday | 2026-03-21 | - | IoT Webapp Development | - | Holiday | - | - | -
|  |  | Eid-ul-Fitr holiday | 2026-03-22
|  |  | Pakistan Day | 2026-03-23
11 | Multi-Device Support & Testing | 2026-03-26 | Review consumer behavior for all active devices | 2026-03-24 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Confirmed that ingestion must remain global while display stays per-device. | -
|  |  | Verify per-device readings API direction | 2026-03-25
|  |  | Plan multi-device DB/UI behavior | 2026-03-26
12 | Data Validation & Normalization | 2026-03-30 | Review invalid JSON handling strategy | 2026-03-27 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 90% | Validation strategy reviewed; structured logging remained a later enhancement. | -
|  |  | Review duplicate payload handling | 2026-03-30
|  |  | Normalize latest-state update logic | 2026-03-30
13 | Latest State & API Development | 2026-04-01 | Improve latest-state consistency | 2026-03-31 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Per-device readings endpoint and latest-state behavior stabilized. | -
|  |  | Fix dashboard readings API routing behavior | 2026-04-01
|  |  | Align API output with dashboard needs | 2026-04-01
14 | Dashboard Reliability & Error Handling | 2026-04-03 | Repair stale realtime dashboard wiring | 2026-04-02 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Dashboard polling and realtime flow made reliable for pilot usage. | -
|  |  | Improve background refresh behavior | 2026-04-03
|  |  | Strengthen failed-refresh and bad-state handling | 2026-04-03
15 | Documentation, Setup & Handoff | 2026-04-08 | Clarify .env usage and MySQL-based setup | 2026-04-06 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Setup guidance and project continuity documents completed. | -
|  |  | Write run instructions and verification flow | 2026-04-07
|  |  | Create full project handoff documentation | 2026-04-08
16 | PPT Analysis, Feasibility & Roadmap | 2026-04-10 | Analyze full project scope vs current codebase | 2026-04-09 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Project direction updated from pilot dashboard to platform roadmap. | -
|  |  | Assess whether full platform is achievable | 2026-04-09
|  |  | Verification | 2026-04-10
17 | Multi-Meter Planning & UX Definition | 2026-04-14 | Define frontend add/remove device behavior | 2026-04-13 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Final UX model approved: store all devices, show only selected device. | -
|  |  | Define delete cascade expectations | 2026-04-13
|  |  | Define selected-device-only dashboard behavior | 2026-04-14
18 | Multi-Meter Implementation | 2026-04-21 | Add selectable dashboard controller flow | 2026-04-15 | Hammaad Ahmad Khalid | IoT Webapp Development | High | In Progress | 90% | Implemented multi-meter dashboard selection and device management; local DB-backed tests require pdo_sqlite to run fully. | If full local automated DB tests are required, install the pdo_sqlite PHP extension.
|  |  | Add device management route/controller/page | 2026-04-16
|  |  | Add create/delete API flow with comments | 2026-04-17
|  |  | Add dashboard selector and realtime filtering | 2026-04-20
|  |  | Add tests and verification updates | 2026-04-21
19 | Final UAT / Closing Window | 2026-04-24 | Verify old and new meter visibility in UI | 2026-04-22 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Pending | 0% | Final user validation window for meter visibility, add/delete flow, and selected-device-only behavior. | If older devices do not appear in UI, verify devices.type = meter and confirm is_active where applicable.
|  |  | Verify add/delete flow plus consumer restart operational step | 2026-04-23
|  |  | Verify selected-device-only dashboard with all-device background ingestion | 2026-04-24
|  |  | Sign-off: end-to-end smoke test across all device flows | 2026-04-28
20 | Core Authentication System | 2026-05-05 | Install and scaffold Laravel Breeze authentication | 2026-04-29 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Full Breeze-based authentication implemented covering login, logout, registration, password reset, email verification, and profile management; sessions and CSRF correctly wired.
|  |  | Implement AuthenticatedSessionController (login/logout) | 2026-04-30
|  |  | Implement RegisteredUserController (registration flow) | 2026-05-01
|  |  | Implement PasswordResetLinkController and NewPasswordController | 2026-05-02
|  |  | Implement EmailVerificationPromptController and VerifyEmailController | 2026-05-03
|  |  | Implement ConfirmablePasswordController and PasswordController | 2026-05-04
|  |  | Build ProfileController and ProfileUpdateRequest | 2026-05-04
|  |  | Scaffold auth Blade views (login / register / forgot-password / reset / verify-email) | 2026-05-05
|  |  | End-to-end authentication flow test | 2026-05-05
21 | Role-Based Access Control (RBAC) | 2026-05-12 | Define role enum (user / admin / super_admin) in codebase | 2026-05-06 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Three-tier role hierarchy (user / admin / super_admin) enforced at migration, middleware, and model levels; backward-compatible isAdmin() retained; custom user profile fields added.
|  |  | Add role column migration to users table | 2026-05-07
|  |  | Implement User model helpers: isSuperAdmin() / isAdminOrAbove() / canAccessDevice() | 2026-05-08
|  |  | Create AdminMiddleware (protects admin+ routes) | 2026-05-09
|  |  | Create SuperAdminMiddleware (protects super_admin-only routes) | 2026-05-09
|  |  | Register and apply middleware to route groups in web.php | 2026-05-10
|  |  | Add custom user fields migration: cnic / phone_number / address | 2026-05-12
22 | User Management Admin Panel | 2026-05-15 | Create UserManagementController (index / create / store / show / edit / update) | 2026-05-13 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Complete admin panel for user management delivered; role assignment and user deletion restricted to super_admin; regular users cannot access any /users/* route.
|  |  | Build users/index.blade.php with search and filter | 2026-05-13
|  |  | Build users/create.blade.php and users/edit.blade.php forms | 2026-05-14
|  |  | Build users/show.blade.php detail view | 2026-05-14
|  |  | Wire role assignment and role promotion routes (super_admin only) | 2026-05-15
|  |  | Implement user delete flow with guard (super_admin only) | 2026-05-15
23 | Device Authorization & Policy | 2026-05-19 | Create DevicePolicy (view / edit / delete / create methods) | 2026-05-15 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Full multi-tenant device isolation implemented; admins bypass ownership checks; regular users see only their own devices; policy applied consistently across web and API routes via Sanctum.
|  |  | Implement canAccessDevice() on User model | 2026-05-16
|  |  | Register DevicePolicy in AuthServiceProvider | 2026-05-16
|  |  | Scope device queries in DeviceManagementController by ownership for non-admins | 2026-05-17
|  |  | Update DeviceManagementController to enforce policy on all actions | 2026-05-17
|  |  | Update API device endpoints (Api/DeviceController) for Sanctum + policy | 2026-05-19
24 | Role-Aware Dashboard & Navigation | 2026-06-01 | Update main DashboardController for role-appropriate statistics | 2026-05-19 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Dashboard and navigation fully role-aware; admins see platform-wide KPIs (total devices/users); regular users see own device summary only; reusable badge and card components built for future scalability.
|  |  | Add admin-only platform-wide stats panel to dashboard.blade.php | 2026-05-20
|  |  | Update layouts/navigation.blade.php with role-gated menu items | 2026-05-21
|  |  | Build role-badge and status-badge Blade components | 2026-05-21
|  |  | Build device-card and stats-card reusable components | 2026-05-22
|  |  | Refine sidebar (sidebar.blade.php) for admin vs regular user views | 2026-05-23
|  |  | Fix DeviceReadingController historical readings and chart API endpoints | 2026-06-01
|  |  | Smoke-test full role-aware flow across all three role tiers | 2026-06-01
25 | Server-Side Pagination for Meter Readings | 2026-06-02 | Add TABLE_PER_PAGE = 100 constant and paginated query mode to DeviceReadingController::index() | 2026-06-01 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Server-side pagination implemented for the meter readings table; 100 rows per page, cursor-based live-refresh mode preserved for backward compatibility; frontend pagination controls and row-range display fully wired.
|  |  | Return { data, meta: { current_page, last_page, per_page, total } } JSON envelope for ?page=N requests | 2026-06-01
|  |  | Preserve backward-compatible cursor/refresh mode (?after_received_at / ?after_id) for live updates | 2026-06-01
|  |  | Add goToPage() function and tablePage / tableTotalPages state variables to meter.blade.php | 2026-06-02
|  |  | Build Previous/Next pagination controls and Page X of Y display in meter dashboard | 2026-06-02
|  |  | Show row range label (Showing rows X to Y of Z total) in readings table header | 2026-06-02
|  |  | Auto-recalculate total pages and prepend new readings to page 1 on realtime push | 2026-06-02
26 | FGAC – Data Layer & Permission Resolution | 2026-07-10 | Phase R: repository hygiene - remove dead MeterDashboardController, stray root files and scratch docs | 2026-07-10 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Delivered with spatie/laravel-permission instead of the originally planned custom permissions + user_permissions tables, Permission model and parametric PermissionMiddleware - the package supplies all four. 30-permission catalog seeded across 5 reusable grant bundles; super_admin bypasses every check via Gate::before. Planned 3-9 Jun, delivered 10 Jul.
|  |  | Phase 0: Redis cache via predis (docker iot-redis) and .env/.env.example deduplication | 2026-07-10
|  |  | Install spatie/laravel-permission and add HasRoles trait to the User model | 2026-07-10
|  |  | Publish config/permission.php and run create_permission_tables migration | 2026-07-10
|  |  | Add Gate::before hook granting super_admin an unconditional bypass | 2026-07-10
|  |  | Make users.role column nullable so legacy role data survives the cutover | 2026-07-10
|  |  | Build PermissionSeeder - 30-permission catalog across 8 feature groups | 2026-07-10
|  |  | Define 5 grant bundles: consumer / prosumer / field_engineer / fleet_operator / super_admin | 2026-07-10
|  |  | MigrateRolesToPermissionsSeeder - map every legacy role enum user onto a bundle | 2026-07-10
|  |  | SuperAdminSeeder - provision the super_admin role and account | 2026-07-10
|  |  | Phase 3: AUTH_ALLOW_REGISTRATION flag - self-serve signups land on the consumer bundle | 2026-07-10
|  |  | RegistrationModeTest - cover both enabled and disabled registration modes | 2026-07-10
|  |  | Document the catalog in docs/FGAC_FEATURES_PERMISSIONS.csv | 2026-07-10
27 | FGAC – Route & Middleware Rewiring | 2026-07-13 | Phase 5: retire role-enum checks - every route and controller now gates on permission slugs | 2026-07-13 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Phase 5 enforcement cutover plus Phase 6 view cutover. Authorization moved off the role enum onto permission slugs at route, controller, policy and Blade level, including the two alerting seams. meter.charts reworked into a per-user opt-in. Legacy role scaffolding deliberately left in place so a single revert could restore prior enforcement. Planned 10-16 Jun, delivered 13 Jul.
|  |  | Gate user management routes with users.view_list / view_profile / create / edit / manage_permissions | 2026-07-13
|  |  | Gate device routes with devices.view_any / create / edit_own / edit_any / delete_own / delete_any | 2026-07-13
|  |  | Gate platform-wide dashboard statistics with dashboard.view_system_stats | 2026-07-13
|  |  | Gate meter dashboard entry with meter.access in DeviceDashboardController | 2026-07-13
|  |  | Gate alert views and per-meter settings with alerts.view_own / view_any / fleet_scope | 2026-07-13
|  |  | Gate API endpoints on the sanctum guard: api.devices.read / api.readings.read / api.devices.write | 2026-07-13
|  |  | Phase 6: view cutover - navigation and sidebar items render only when permitted | 2026-07-13
|  |  | Gate meter dashboard sections independently: meter.live_data / meter.charts / meter.history | 2026-07-13
|  |  | Remove meter.charts from the consumer bundle - becomes a per-user opt-in grant | 2026-07-13
|  |  | Scope meter.charts to the five live charts; reporting panels remain basic | 2026-07-13
|  |  | MeterSectionPermissionsTest - assert granted vs denied for every dashboard section | 2026-07-13
|  |  | Regression: confirm super_admin flows and the MQTT ingestion pipeline are unaffected | 2026-07-13
28 | FGAC – Privilege Management UI | 2026-07-10 | Phase 4: build PermissionController (show / update) for the per-user Manage Access screen | 2026-07-10 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Manage Access screen delivered as Phase 4: bundle membership plus direct per-user grants, with super_admin rows locked against modification. Audit metadata is carried by the spatie pivot rather than the custom granted_by/granted_at columns first planned. Planned 17-23 Jun, delivered 10 Jul.
|  |  | Add routes GET and PATCH /users/{user}/permissions under the role:super_admin group | 2026-07-10
|  |  | Build users/permissions.blade.php - permission toggles grouped by feature area | 2026-07-10
|  |  | Render bundle membership alongside direct per-user grants on the same screen | 2026-07-10
|  |  | Surface a permission summary column on users/index.blade.php | 2026-07-10
|  |  | Show granted permissions plus a Manage Access link on users/show.blade.php | 2026-07-10
|  |  | Guard: super_admin permission sets cannot be modified through the UI | 2026-07-10
|  |  | Guard: users.manage_permissions kept behind the super_admin route group | 2026-07-10
|  |  | PermissionManagementTest - cover grant and revoke flows end to end | 2026-07-10
|  |  | Verify a revoked permission denies access on the very next request | 2026-07-10
|  |  | Write docs/PERMISSIONS_HANDBOOK.md describing bundles and every slug | 2026-07-10
|  |  | Full regression across super_admin flows after the UI lands | 2026-07-10
29 | Meter Consumption, Reporting & Alerting Platform | 2026-07-06 | Create meter_monthly_consumption and meter_daily_consumption rollup tables | 2026-06-30 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Two-part delivery: consumption rollups and range reporting (30 Jun), then the alert delivery pipeline and opt-in triggers (6 Jul). Alerts require three consecutive breaching scans before opening and three clear scans to resolve, so transient spikes never fire. Deliberately deferred: real mail transport - MAIL_MAILER=log today, so the in-app bell works but email needs SES/Postmark.
|  |  | Build MeterDailyConsumption model and the CloseMeterDay scheduled command | 2026-06-30
|  |  | BackfillDailyConsumption command to populate rollups from historical readings | 2026-06-30
|  |  | RangeConsumption service - reset-safe energy deltas across any time window | 2026-06-30
|  |  | Accrue consumption inside MeterPayloadProcessor on every valid reading | 2026-06-30
|  |  | Add daily and monthly consumption report panels to the meter dashboard | 2026-06-30
|  |  | Rename meter_alert_events to alert_events and introduce the AlertEvent model | 2026-07-06
|  |  | Alert delivery pipeline: AlertOpened / AlertResolved events + EnqueueAlertForDelivery listener | 2026-07-06
|  |  | Create notifications, notification_preferences and pending_alert_notifications tables | 2026-07-06
|  |  | DispatchAlertDigests command with AlertDigestNotification and per-user preferences | 2026-07-06
|  |  | Opt-in threshold triggers: ScanThresholdAlerts with three-consecutive-scan debounce | 2026-07-06
|  |  | Opt-in consumption triggers: ScanConsumptionAlerts over the daily rollups | 2026-07-06
|  |  | PruneAlertsAndNotifications retention command and MeterAlertSettingsController opt-in UI | 2026-07-06
30 | Simplified Consumer Dashboard & Hourly Rollup | 2026-07-15 | Create the meter_hourly_consumption rollup table | 2026-07-14 | Hammaad Ahmad Khalid | IoT Webapp Development | High | Completed | 100% | Product decision 2026-07-14: consumers get a simplified dashboard (4 KPI tiles plus aggregated hour/day usage history) while raw minute-level readings become prosumer/operator-only, enforced in both the view and the API so hand-crafted requests cannot bypass it. Hourly rows prune at 180 days and older windows degrade to day buckets automatically. Approved by CEO 15 Jul.
|  |  | Build MeterHourlyConsumption model and accrue hourly buckets in MeterPayloadProcessor | 2026-07-14
|  |  | BackfillHourlyConsumption and PruneHourlyConsumption (180-day retention) commands | 2026-07-14
|  |  | Add the meter.full_dashboard permission slug to the prosumer bundle | 2026-07-14
|  |  | Route DeviceDashboardController on User::hasFullMeterDashboard() | 2026-07-14
|  |  | Build meter-simple.blade.php - 4 KPI tiles plus click-to-expand usage history | 2026-07-14
|  |  | Add GET /api/devices/{device}/readings/aggregate serving hour and day buckets | 2026-07-14
|  |  | Restrict raw minute-level readings to full-dashboard users in the view AND the API | 2026-07-14
|  |  | MeterSimpleDashboardTest - cover the consumer view and the aggregate endpoint | 2026-07-15
|  |  | Update PERMISSIONS_HANDBOOK.md and FGAC_FEATURES_PERMISSIONS.csv to the 30-slug catalog | 2026-07-15
31 | FGAC Phase 7 - Legacy Role Removal | TBD | Drop the users.role column and retire its migrations |  | Hammaad Ahmad Khalid | IoT Webapp Development | High | Pending | 0% | Phase 7 of docs/FGAC_IMPLEMENTATION_PLAN.md. The legacy role scaffolding was intentionally kept through Phases 5-6 so a single git revert could restore prior enforcement. Now that permissions gate every request it is dead weight and can be removed. | Confirm no external integration or report reads users.role before the column is dropped.
Delete AdminMiddleware and SuperAdminMiddleware
Remove User role helpers: isAdmin() / isSuperAdmin() / isAdminOrAbove()
Remove updateRole() and the role dropdowns from user management screens
Delete components/role-badge.blade.php
Remove the /devices/manage redirect route left over from Phase 6
32 | FGAC Phase 8 - Guardrails & Documentation | TBD | Add a CI guardrail test asserting the seeded bundle snapshot to catch silent drift |  | Hammaad Ahmad Khalid | IoT Webapp Development | High | Pending | 0% | Phase 8 of docs/FGAC_IMPLEMENTATION_PLAN.md - the closing phase. Locks the permission catalog against silent drift in CI and brings the documentation set in line with the shipped system.
Add a CI check that no route still relies on the legacy role middleware
Rewrite PROJECT_HANDBOOK.md around the permission model
Close out the FGAC section of docs/PENDING_WORK.md
Update use-case.md UC26 to describe the Manage Access flow
Mark docs/FGAC_IMPLEMENTATION_PLAN.md as implemented